## Gantt Chart
Machine | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6
Press-10T | Task 1: Time: 9:00 AM - 9:07 AM Part No.: Hinge Plate Operation: Bending Task: Die Setting; Task 2: Time: 9:07 AM - 10:19 AM Part No.: Hinge Plate Operation: Bending Quantity: 300
Press-20T | Task 1: Time: 9:00 AM - 9:08 AM Part No.: Hinge Plate Operation: Blanking Task: Die Setting; Task 2: Time: 9:08 AM - 10:26 AM Part No.: Hinge Plate Operation: Blanking Quantity: 300
Press-30T | Time: 9:00 AM - 9:05 AM Part No.: A-Pillar Stiffener Operation: Draw Task: Die Setting | Time: 9:05 AM - 10:05 AM Part No.: A-Pillar Stiffener Operation: Draw Quantity: 300 | Time: 10:15 AM - 10:20 AM Part No.: A-Pillar Stiffener Operation: Punching Task: Die Setting | Time: 10:20 AM - 10:50 AM Part No.: A-Pillar Stiffener Operation: Punching Quantity: 300 | Time: 11:00 AM - 11:05 AM Part No.: Engine Mount Bracket Operation: Bending Task: Die Setting | Time: 11:05 AM - 11:45 AM Part No.: Engine Mount Bracket Operation: Bending Quantity: 400
Press-30T-2
Press-50T | Time: 11:20 AM - 11:25 AM Part No.: Engine Mount Bracket Operation: Drawing Task: Die Setting | Time: 11:25 AM - 12:45 PM Part No.: Engine Mount Bracket Operation: Drawing Quantity: 400 | Time: 1:10 PM - 1:15 PM Part No.: Engine Mount Bracket Operation: Trimming Task: Die Setting | Time: 1:15 PM - 2:19 PM Part No.: Engine Mount Bracket Operation: Trimming Quantity: 400 | Time: 2:44 PM - 2:49 PM Part No.: Engine Mount Bracket Operation: Punching Task: Die Setting | Time: 2:49 PM - 3:45 PM Part No.: Engine Mount Bracket Operation: Punching Quantity: 400
Press-50T-2
Press-75T | Time: 9:00 AM - 9:10 AM Part No.: Engine Mount Bracket Operation: Drawing Task: Die Setting | Time: 9:10 AM - 11:10 AM Part No.: Engine Mount Bracket Operation: Drawing Quantity: 400 | Time: 11:25 AM - 11:30 AM Part No.: A-Pillar Stiffener Operation: Draw Task: Die Setting | Time: 11:30 AM - 12:30 PM Part No.: A-Pillar Stiffener Operation: Draw Quantity: 300
Press-75T-2
Press-100T
Press-150T
Press-200T
Press-250T
Press-300T

## Dashboard
Machine Utilization
Machine | Utilization (%) | Busy Time (min) | Idle Time (min)
Press-10T | 14.26 | 77 | 463
Press-20T | 15.56 | 84 | 456
Press-30T | 35.19 | 190 | 350
Press-30T-2 | 0.00 | 0 | 540
Press-50T | 57.78 | 312 | 228
Press-50T-2 | 0.00 | 0 | 540
Press-75T | 40.74 | 220 | 320
Press-75T-2 | 0.00 | 0 | 540
Press-100T | 0.00 | 0 | 540
Press-150T | 16.67 | 90 | 450
Press-200T | 0.00 | 0 | 540
Press-250T | 0.00 | 0 | 540
Press-300T | 0.00 | 0 | 540
Part Production Summary
Part Name | Target Quantity | Quantity Produced
Engine Mount Bracket | 400 | 1600
A-Pillar Stiffener | 300 | 1200
Hinge Plate | 300 | 600

## Production Matrix
Part Name | Target | Bending | Blanking | Draw | Drawing | Punching | Trimming | Total Finished Parts | 1 Drawing | 2 Drawing | 1 Draw | 2 Draw
Engine Mount Bracket | 400 | - | - | - | - | - | - | - | - | -
A-Pillar Stiffener | 300 | - | 300 | - | - | - | - | - |  |  | - | -
Hinge Plate | 300 | 300 | 300 | - | - | - | - | 300

## Detailed Plan
Part Name | Operation | Task Type | Machine | Quantity | Cumulative Quantity Produced | Start Time | End Time | Duration (min) | Operator Name | Actual Quantity
Engine Mount Bracket | (Target: 400)
| Drawing | Die Setting | Press-75T |  |  | 9:00 AM | 9:10 AM | 10
| Drawing | Production | Press-75T | 400 | 400 | 9:10 AM | 11:10 AM | 120
| Drawing | Die Setting | Press-50T |  |  | 11:20 AM | 11:25 AM | 5
| Drawing | Production | Press-50T | 400 | 800 | 11:25 AM | 12:45 PM | 80
| Trimming | Die Setting | Press-50T |  |  | 1:10 PM | 1:15 PM | 5
| Trimming | Production | Press-50T | 400 | 400 | 1:15 PM | 2:19 PM | 64
| Punching | Die Setting | Press-50T |  |  | 2:44 PM | 2:49 PM | 5
| Punching | Production | Press-50T | 400 | 400 | 2:49 PM | 3:45 PM | 56
| Bending | Die Setting | Press-30T |  |  | 11:00 AM | 11:05 AM | 5
| Bending | Production | Press-30T | 400 | 400 | 11:05 AM | 11:45 AM | 40
A-Pillar Stiffener | (Target: 300)
| Blanking | Die Setting | Press-160T |  |  | 9:00 AM | 9:10 AM | 10
| Blanking | Production | Press-160T | 300 | 300 | 9:10 AM | 10:40 AM | 90
| Draw | Die Setting | Press-30T |  |  | 9:00 AM | 9:05 AM | 5
| Draw | Production | Press-30T | 300 | 300 | 9:05 AM | 10:05 AM | 60
| Draw | Die Setting | Press-75T |  |  | 11:25 AM | 11:30 AM | 5
| Draw | Production | Press-75T | 300 | 600 | 11:30 AM | 12:30 PM | 60
| Punching | Die Setting | Press-30T |  |  | 10:15 AM | 10:20 AM | 5
| Punching | Production | Press-30T | 300 | 300 | 10:20 AM | 10:50 AM | 30
Hinge Plate | (Target: 300)
| Blanking | Die Setting | Press-20T |  |  | 9:00 AM | 9:08 AM | 8
| Blanking | Production | Press-20T | 300 | 300 | 9:08 AM | 10:26 AM | 78
| Bending | Die Setting | Press-10T |  |  | 9:00 AM | 9:07 AM | 7
| Bending | Production | Press-10T | 300 | 300 | 9:07 AM | 10:19 AM | 72